## Slide 1
Organized and hosted by
International Tsunami Information Center
Dr. Laura Kong, Director, US NOAA
Cdr. Carlos Zuniga, Associate Director, Chile SHOA
Christa von Hillebrandt, Deputy Director, Manager ITIC Caribbean Office
ICG/PTWS Post-Event Brief III: 15 January 2022, Hunga-Tonga Hunga-Ha'apai Volcanic Eruption and Tsunami
ACTIONS FORWARD

## Slide 2
ACTIONS FORWARD – Brief I (20 Jan 2022)
Interim Tonga Volcano Guidance
  PTWS WG 2 (Detection, Warning, Dissemination) lead, per their Terms of Reference
  Urgent priority since could happen again anytime
  To Fast track, work in parallel:
    Implementation will begin immediately
      By Member States based on their national process
      By PTWC based on today’s proposal. Expect to implement most urgent in 1 week. PTWC test to TWFP/NTWC before start
    Use PTWS govermance process to make official
      WG 2 to formulate written ‘proposal’ (including implementation plan).
        Describes criteria, products, dissemination, procedures, country guidance, etc.
        ‘Proposal’ will be ’living document’ until finalized
      WG 2 sends to PTWS SC to approve. Then, SC sends to ICG/PTWS-XXX (Nov 2022) recommending approval. IOC MS approve ICG/PTWS-XXX recs
      IOC informs Member States by Circular Letter
  Request TOWS-WG TT-TWO TT on Atypical sources (TT-AS, Francois Schindele chair) to consider Tonga situation. TT-AS may take several years to do its work (review monitoring/warning success of Italy, Indonesia
IOC Post-Event Assessment Questionnaire Survey (TOWS-WG-VIII, APP V, 2015) (online) – expect IOC CL next week
Post-Event Brief II – Feb 3, same time

## Slide 3: Tonga - Recommendations for warning center
Review SOPs to include more detail in volcano generated tsunami and warnings
Volcanology training for warning personnel (should we have canceled the Tsunami Marine Warnings at 10am on Saturday?)
Establish a study group under the PTWS to research into exactly what happened (e.g. resulting in loss of life in Peru) and for PTWC to finalize regional procedures for quick advisory services for near source volcano generated tsunami
Awareness on natural warning signs (e.g. the Sulphur smell)
Establish better communication redundancies
Establish better communication protocols to address congested lines
Improve seismic network and volcano monitoring
Reconsider working arrangements with national response agencies e.g. to be under one roof

## Slide 4: ACTIONS FORWARD – BRIEF III (10 Feb 2022)
PTWS Interim Procedures Implementation Plan for HTHH Volcanic Tsunami Hazard – request PTWS SC action
Countries to develop HTHH Volcanic Tsunami Hazard Response Plan (TWC, DMO)
Country NTWCs to develop SOPs under different data scenarios (no PTWC, no comms, etc ???)
Make sure contact information is up-to-date
For non-seismic sources, sea level monitoring essential.
  All sea level data should be shared.
  All NTWC should know how to access sea level data in real time for decision-making
  All NTWC should understand the difference between coastal and DART data, and how to interpret – ITIC working with PTWC, PMEL, NZ, Chile, etc

## Slide 5: ACTIONS FORWARD – BRIEF III (10 Feb 2022)
Regional coordination and sharing valuable
  Familiarity and development of common protocols and SOPs
  During an event, valuable to share what each other is observing (sounds, eyewitness), issuing (bulletins, alerts), interpretations, etc
  Consider sharing between NTWCs (such as SEP, CA-PAC) – dedicated social media group, hotline, chat, or other means
  Conduct regional exercise (such as SEP) to practice info sharing
Update PTWS Local SOP (June 2019) to include Volcanic sources
Emphasize and Action Pre-event Preparedness, such as UNESCO IOC Tsunami Ready