## Slide 1
IOC Group of Experts on Capacity Development
5th Session
27-29 February 2024
Paris
Agenda 7 Workplan
Alan Evans

## Slide 2
PROPOSED WORKPLAN
TASKS | Assigned Roles/Contributors | Timeline
As discussed under agenda item 2.2, the following tasks relating to the Ocean CD-Hub: |  | 
Organize and conduct regional webinar series as part of outreach and promotion of the new IOC CD Strategy 2023-2030 and the utilization of the Ocean CD-Hub | RSB Secretariats and CD Secretariat | 
Contribute entries to the Ocean CD-Hub by submitting details of related CD initiatives of their organizations/countries | GE-CD | 
As discussed under agenda item 2.3, the following tasks relating to the 4th CD needs assessment survey: |  | 
Draft the design and methodology and development of survey questionnaires | CD Secretariat/RSB Secretariats | March – April 2024
Identification of targeted key stakeholder respondents | RSB Secretariats | March – April 2024
Review and approve the survey | GE-CD | June 2024
Conduct of the survey | CD Secretariat (CL) and RSB Secretariats | June – July 2024
Analysis | CD Secretariat (overall); RSB Secretariats (regional) | August – September 2024
Report to the GE-CD | CD Secretariat | October 2024
As discussed under agenda 3.1 – 3.3, the following tasks relating to instructions by the IOC-XXXII Assembly: |  | 
Revised GE-CD ToRs approved by the EC, call for GE-CD membership renewal | CD Secretariat (CL) | June 2024
New GE-CD membership inaugurated, WG on Implementation Plan established | New GE-CD (WG on Implementation Plan) | September 2024
Draft CD workplans presented to GE-CD | RSB Secretariats & Global programmes | September 2024
Working Group to start on drafting implementation plan | GE-CD Working Group | October – December 2024
Review and submission of implementation plan | GE-CD | February 2025
(i) develop programmatic and regionally relevant capacity development work plans based on this strategy and related needs assessments conducted in a consistent manner, building on on-going activities and making use of existing training and education facilities; (to be submitted to the IOC-XXXIII Assembly) | CD Secretariat | April 2025 (Submission of documentation for the Assembly in June 2025)