GOOS Network OCG-15

GOOS Ocean Gliders

Brad deYoung

- Highlight the key network successes

- Expansion of OceanGliders: The OceanGliders program is expanding globally, with significant potential for growth in Asia, Europe, and Canada that remains under-monitored.

- Enhanced Program Coordination: Centralization of glider programs in Australia and the USA has streamlined activity monitoring, with both regions fully integrated into the program.

- Achieving Targets by 2030: Program goals are attainable by 2030 through improved member engagement and efficient data management (OG1.0).

- How has the network advanced across the OCG Network Attribute areas

- Program Development and International Expansion: The program's expansion into Asia, with Korea and China joining the Steering Team, is a essential for its internationalization.

- New Task Teams: Introduction of new task teams including Polar Task Team, Data Assimilation Task Team, and Passive Acoustic Monitoring Task Team enhances program capabilities.

- Structured Program Development: The program is structuring around a GitHub repository hosting data management formats, controlled vocabularies, the BOON team, and Standard Operating Procedures (SOPs) (including vertical velocities recently integrated).

- OG1.0 Implementation: OG1.0 implementation, approved by the Data Assembly Centers, is set for official release (delayed due to consensus issues) by June 2024 at an international meeting.

- Future Plans and Opportunities - at network and/or cross-network OCG level

- Achievable Targets by 2030: OceanGliders aims for ambitious targets by 2030, including 1000 missions annually with 100 gliders deployed continuously at sea.

- Rationalizing Program Monitoring: Efficient monitoring of this growing program requires rationalization and robust community support, which is currently no enough.

- Implementation of OG1.0: Adoption and implementation of OG1.0 will be pivotal in achieving these objectives.

- Challenges and Concerns - at network and/or cross-network OCG level

- Support for Increased Monitoring Capacity: Adequate funding is essential to enhance monitoring capacity (instrumentation, data flow, and fleet performance). Currently, only one country provides regular funding for OceanGliders beyond project-based support.

- Exploring Funding Mechanisms: Exploring mechanisms to secure funding through organizations (WMO or IOC) is crucial. Collaborative funding models, such as sharing mechanisms with Argo, could offer viable solutions.

- Asks from OCG (Exec, networks, OceanOPS, and/or GOOS), perhaps related to the responses to parts 3 and 4 and how OCG can support your network

- Exploring Funding Mechanisms: Exploring mechanisms to secure funding through organizations (WMO or IOC) is crucial. Collaborative funding models, such as sharing mechanisms with Argo, could offer viable solutions.

- Recent publications, articles, etc. (if you want to share)

- None directly from Ocean Gliders, lots on gliders.

https://oceanexpert.org/downloadFile/45372

Future plans on implementation, instrumentation, data management, test, new sensors, plan for new EOV/ECV observations, capacity development, etc.