## Slide 1
May 13, 2024, Paris
Presenter: Derya Itir VENNIN, PhD
Assoc. Project Officer UNESCO IOC/TSR
CoastWAVE Project Coordinator
d.dilmen-vennin@unesco.org
Progress Summary
Funded by the European Union (EU) Directorate-General for European Civil Protection and Humanitarian Aid Operations (DG ECHO)
COASTWAVE PROJECT

## Slide 2: COMPONENT 2 (Tsunami Detection and Alerting Equipment ) Remaining Activities
Activity | Completed
Activity 1 Identify local partners to operate and maintain the systems | El Jadida-Governor of EL Jadida Alexandria- Governor of Alexandria Chipiona- Municipality of Chipiona Cyprus- Cyprus Civil Defence
Activity 2 Conduct site surveys to identify optimum locations for the tsunami detection and alerting systems | Partners identified the operating agencies responsible for handling and maintaining the systems . Performed site surveys Currently being completed by the companies and the local partners in Alexandria and El Jadida
Activity 3 Design, installation and commissioning of the tsunami detection and alerting systems | TOR established for the affordable tide gauges in collaboration with JRC TOR established based on FEMA guidelines for the sirens Advertised and followed the procurement procedures of UNESCO Designed, procured and installed 3 Affordable Tide Gauges (ATG) in Morocco, Cyprus and Egypt by Universitat de les Illes Balears and Spanish Institute of Oceanography. Needs determined by the companies and the local partners for the sirens: 2 electronic sirens-El Jadida 3 electronic sirens-Alexandria 2 electronic sirens-Chipiona 3 electronic sirens-Cyprus

## Slide 3
REMAINING ACTIVITIES
May
Final project meeting in Alexandria, 27-30 May 2024
Installation of signages and alert systems in Cyprus, Morocco, Egypt and Spain
20
24
June
TR ceremonies of Morocco, Greece and Spain
External Evaluation of the project by the auditors
20
24
July
External Evaluation of the project by the auditors
Final reporting
Publications on Risk perception and IDSL
20
24
August
External Evaluation of the project by the auditors
Summary brochures
20
24
September
External Evaluation of the project by the auditors
20
23
October
Final closure after the review of the external evaluation
2024
80%
85%
90%
95%
97%
99%

## Slide 4
Thank you for your attention.
DERYA VENNIN, PHD
d.dilmen-vennin@unesco.org
coastwaveproject
CoastWave_IOC