## Slide 1
ICG/PTWS WG3 Task Team on Tsunami Ready July 2024
PTWS WORKING GROUP 3
ON DISASTER RISK MANAGEMENT AND PREPAREDNESS (WG 3)
TASK TEAM ON TSUNAMI READY
NEXT STEPS

## Slide 2
Next Steps
ICG/PTWS WG3 Task Team on Tsunami Ready July 2024
Date | Meeting | Equivalency Guidance | TR Implementation Survey
July 2024 | TT TR Meeting 1 | Discuss path forward | Discuss path forward
August 2024 (propose 21 Aug) | TT TR Meeting 2 | Discuss progress on drafting of process and reporting template. | Discuss progress on drafting of Survey
September 2024 | ICG/PTWS SC | Report on progress. Request Regional Working Group feedback in coming month. | Seek approval to run Survey before ICG/PTWS in April
February 2025 | TOWS-WG-XVIII | Progress on TR Equivalency shared with TOWS WG / TT-DMP | 
April 2025 | PTWS-XXXI | TR Equivalency approved at ICG/PTWS-XXXI | Present results of Survey
June 2025 | IOC Assembly | PTWS reports approval of TR Equivalency | 
February 2026 | TOWS-WG XIX | PTWS TR Equivalency presented to TOWS WG / TT-DMP for global consideration |