# **2024 OBPS WORK PLAN -**  beige out = requires EXB funding

| **Work Package** | **Strategic Objective** | **Task** | **Due Date** | **STATUS** **@ 13 March 2024** | **STATUS****@ 19 June 2024** | **STATUS****@ 18 Sep 2024** | **STATUS****@12 Nov 2024** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WP2 | S0-01.1 | A1.1. Secure a CORE Trust Seal Repository Certification | Unlikely until 2025 | No IOC funding available, only possible if funded EXB | No IOC funding available, only possible if funded EXB | No IOC funding available, only possible if funded EXB -Possible candidate for 2025 budget | No IOC funding available, only possible if funded EXB -Possible candidate for 2025 budget |
| WP2 | S0-01.2 | A1.2 AI Translation (DeepL or other non AI ) additional endorsed practices (6 of 11 already done) | 2024-12 | No IOC funding available, only possible if funded EXB | No IOC funding available, only possible if funded EXB | No IOC funding available, only possible if funded EXB - possibly not a priority | No IOC funding available, only possible if funded EXB - possibly not a priority |
| WP2 | S0-01.3 | Investigate such as NiMMbus for repository user feedback and interactive dialogue with BP creators | 2024-12 |  | Progress through the external contracts (ETT, CINEA) | Progress through the external contracts (ETT, CINEA) | Item included on 2025 work plan/budget for contractor to implement a mechanism  |
| WP2 |  | Enhance document inclusion policy in existing Repository Policies and guidelines for submission | 2024-04 | IN PROGRESS | COMPLETED  | COMPLETED  | COMPLETED |
| WP2/3 | S0-01.3 | A1.4. Review of documenttemplate style andcompleteness. | 2024-09 | 4 templates exist with updated metadata profiles and a separate collection in the repository holding OBPS and other org. templates. Need discipline experts to work with for new templates  | Need to identify discipline experts willing to work on new templates  | DTO Template commenced Sep 2024 | Ongoing exercise |
| WP3 | S0-01.3 | A1.3. Create improved content browsing and discovery functions through decision tree methods | 2024-09 | there will be paper in 2/2024 where they will identify process to implement 3 tasks/ to report to SG mid-2024 | Being addressed through CINEA Project | Being addressed through CINEA Project. Tools from the Decision Tree TT planned to assist practice discovery/choice | Being addressed through CINEA Project. In addition, the Content criteria and Tools from the Decision Tree TT should assist practice discovery/choice  |
| WP3 | S0-01.4 | A1.4. Expand BP submission processes to include **automated submission - Autoingest of metadata** (Journal) CrossRef sub+ TDM/API implementation  | 2024 | No IOC funding available, only possible if funded EXB | No IOC funding available, only possible if funded EXB | No IOC funding available, only possible if funded EXB | No IOC funding available,in work plan/budget 2025 but only possible if funded EXB |
| WP3 | S0-01.5 | A1.5. Create, enhance and expand machine-readable templates offered by the OBPS to cover methodology types submitted | 2024 | No IOC funding available, only possible if funded EXB | No IOC funding available, only possible if funded EXB(see also SO-01-3) | No IOC funding available, only possible if funded EXB(see also SO-01-3) | No IOC funding available,in work plan/budget 2025 but only possible if funded EXB |
| WP3 | S0-02.2 | A2.3. Expand enhanced search including semantic capabilities to accommodate broader range of disciplines, languages and cultures | 2024 **Upload ASFA and WoRMS to EDS** | No IOC funding available, only possible if funded EXBE84 supplied the instructions August 2023, but upload not tested. IT Support has been requested to test | Included in the current ETT Enhancement contract | Not yet started - issues with AWS/EDS | Not yet started - issues with AWS/EDS |
| 2024EOV Vocabulary uploaded to deposit interface | PLB offered to do this in 2023 but not so far.. Who can take this on? | Progressed through CINEA in collaboration with BODC.In the meantime ETT enhancement contract is implementing an EOV select and populate the metadata on the input interface. | EOV vocabulary ready to be uploaded to deposit interface, waiting for IODE IT  | EOV vocabulary implementation script ready to be uploaded to deposit interface, waiting for IODE IT to solve problem with staging server |
| WP3 | SO-04.1 | A4.1. Design a federation approach, to a global collection of independent methodology management systemsA4.2. Develop a pilot demonstration of a federated system so that queries across partner systems enable access to best-practices methodology content hosted elsewhere | -2024-07 | COMPLETEDOcean Practices Federated Network In progress .- Aquaculture and Fisheries Pilot and OPFN portal | COMPLETEDFUST proposal was rejected. A new funding line needs to be established to move forward with development of Pilot. | COMPLETEDSeeking other EXB funding opportunities | COMPLETED |
| WP4 | SO-02.1 | Endorsement Process Guidance Document | 2024-03 | COMPLETED | COMPLETED | COMPLETED | COMPLETED |
| WP4 | SO-02.1 | Endorsement Process Infographic | 2024- | IN PROGRESS | COMPLETED | COMPLETED | COMPLETED |
| WP5 | SO-02.3 | A2.5. Host annual workshops | 2024-10 | Organising Committee and Co-Chairs commenced planning | In progress for 14-18 Oct 2024 ONLINE | In progress for 14-18 Oct 2024 ONLINE | COMPLETED |
| WP7 | SO-03.3 | A3.1 Training resources provided by OTGA and other training providers available through the OBPS repository (ADAPT).A3.3 Engage formal and informal education institutions and sponsors to advance incorporation of best practices for ocean observing into education curricula | 2025-052024-12 | Waiting for ADAPT Consultancy Contract to be completed.  | Work in progressProfessors were contacted. 3 meetings to discuss the initiative were carried out. OBPS learning materials are being reviewed to prepare classes for a first try out in the second semester.  | Project contract issues have delayed progress | Delay continues |
| WP8 | SO-04 | Survey of Ocean Practices Partners on continued commitment and contribution | 2024 |  | In progress for Oct 2024 | In progress for Oct 2024 | ? |
| WP8 |  | Ocean Practices for the Decade - Video , flyer, poster  | 2024 | No IOC funding available, only possible if funded EXB.Rebecca may try to create a short video for Barcelona 2024 | In progress for Dec 2024 | In progress for Dec 2024, potentially to involve volunteers for this task | ? |