## EW4ALL GMSF Time LIne
EWF4ALL |  | Progress | TS1: Gender-responsive and disability-inclusive EW EAA
| Global EW4All Multi-Stakeholder Forum , 2-3 June 2025, Geneva | Done | TS2: Enable and scaling of community-led EWS, including FCV | Co-Lead
May-July 2024 | Proposal of Global Forum Themes | Done | TS3: Nationally-led and user-tailored EW-EAAs
2024-09-01 | Agenda Develoment | Done | TS4: Increase investments in EWS
2024-10-01 | Selection of session focal point. Deadline 26 Nov | In Progress | TS5: Fostering international and regional cooperation and partnerships | Co-Lead
Nov-Dec 2024 | Development of Session Concept Note |  | TS6: Common Alerting Protocols and Private sector partnerships for risk communication
Dec-Jan 205 | Identification of Speakers |  | TS7: Leverage science, technology and innovation to advance EWS
| Finalisation of Session and Speaker Invites |  | TS8: Delivering local anticipatory action
Feb-May 2025 | Speaker and Sesion Preparation
June | In session Management
Follow up
| Regional Early Warnings for All MSFs | Nominated Regional Contact IOC Officer
| Regional MSF at the Asia Pacific Regional Platform for DRR –Manila, the Philippines | Ardito Kodijat & Ocal Necmioglu
| 14-17 October 2024 | Adewumi, Ibukun
| Regional MSF at the High-Level Ministerial Meeting of the 13th Caribbean Comprehensive Disaster Management ConferenceNevis –St Kitts andNavis,02-06 December 2024 | Inniss, Lorna Veronica
| Regional MSF at the Regional Platform for DRR - Arab States Kuwait City, Kuwait, Feb 2025 | Denis Chang Seng

## EW4ALL Organising Commitee
Organising Committee Members
UNDRR & WMO
ITU
IFRC
CREWS
REAP
UNDP
UNEP
FAO
OCHA
UNESCO | Denis (IOC)and Soichiro (DRR Unit)
WFP
SEM
GNDR
EOSG CAT

## GPDRR2025 IOC
GPDRR, 2-6 June 2025
Engagment Level |  | Proposed event | Lead | Remarks | Partners | Concept Note | Speakers | Logistics
1 | Main Event-HighLevel Dialogue | 20 Years of Developing the Tsunami Early Warning and Mitigation System. | Denis/Srinivas Kumar/Also at One Ocean at the same time? | On Standby. Email sent to Regina on 18th october and follow up later | UNDRR |  | IOC Executive Sec
2 | Side Event | Increasing Coastal Community Disaster Resilience through Machine Learning and Innovative Observing Systems to Scale Up and Transform Early Warning Systems for 4th June. | Denis Chang Seng/BA/Ocal | Not approved. All 3 UNESCO DRR Unit propisal delcined too | ODTP Action Partners |  | Denis
3 | Innovation Platform
4 | Ignite Satge | 1. Coastal Resilience in DRR (CoastWAVE Project Contribution) | Derya Vennin | Submitted/waiting |  |  | Derya
|  | 2 | Ardito Kodijat | Submitted/waiting |  |  | Ardito