## Slide 1: 1st Online Meeting IOC-SOPM Working Group
Tuesday 9 December 2025
15:00-16:30 CET
IOC-wide Strategy 2025-2030
Sustainable Ocean Planning and Mangement
& Implementation Plan 2025-2027

## Slide 2: Adoption of the Agenda
1 Introduction
Terms of Reference of the Working Group
Election of Co-chairs
Adoption of the Agenda
Presentation/discussion Work Plan & milestone deliverables Implementation Plan 2025-2027 + Task Force Groups
Any Other Business
Closure of the Meeting

## Slide 3: Terms Of Reference Working Group
Decision A-33/4.1
Monitor implementation of the SOPM Strategy & Implementation Plan, including guidance in the regular assessment of user-needs in the area of SOPM
Update the SOPM Strategy, linking the results of the ‘IOC and the Future of the Ocean Consultations’ and Implementation Plan 2028-2030
Advise on identifying emerging needs and science, data and knowledge issues with potential implication for SOPM practitioners
Advise on the design and delivery of IOC activities in support of the SOPM Strategy
Advise on the IOC Contribution to the UN Ocean Decade Programme on SOP
Advise on the ‘IOC and the Future of the Ocean’ Consultation process 2024-2027, as it relates to SOPM
Provide inputs to the development of the IOC Medium-Term Strategy processes, to be initiated in 2027
Undertake any endeavor as requested by the IOC Governing Bodies

## Slide 4: Election of Co-Chairs
Candidates
Ms. Marinez Scherer, PhD
Associate Professor
Federal University Santa Catarina, Brazil
Mr. Gunnar Finke
Ocean Team Leader
German International Cooperation Agency (GIZ)

## Slide 5: SOPM Strategy Implementation Plan 2025-2027
Adoption at 33rd session IOC General Assembly: IOC/A-33/4.1.Doc(1)
Implementation Plan period mid 2025-end 2027
Reporting to the 34th session of the IOC General Assembly (June-July 2027)
Five Expert Working Group meetings:
  December 2025 (online)
  February-March 2026 (online)
  Oct-Nov 2026 (in person)
  March-April 2027 (online)
  Nov-Dec 2027 (online)

## Slide 6: Vision, Mission & Outcomes
Vision
IOC Member States equipped to implement knowledge-based SOPM
Mission
Support decision-makers by facilitating data uptake, advancing knowledge products, and strengthening capacities by 2030
Expected Outcomes
Science-based SOPM policy approaches
Integration of ocean data & knowledge
Coherence across sectors & boundaries
Increased stakeholder capacity
Climate & Biodiversity integration

## Slide 7: Key Activities
A1: Identify decision-makers & engagement mechanisms
A2: Develop communication plan & multilingual outreach materials
What, how, why, when of SOPM & role of IOC
A3: End-user consultations & reporting on science, data needs & gaps
A4: Review SOPM Initiatives, develop/implement technical guidance & capacity development plan
A5: Concept & ToR for SOPM pilot project in Member States
+ Fundraising & partnership establishment

## Slide 8: Work Plan & Timeline
Fundraising & partnership building throughout Q3 2025-Q4 2027
Complete communication plan, outreach materials & initial good practices summarized by Q2 2026
Technical guidance & best practices by Q3 2026
Start pilot project Member States by Q4 2026
Organize regional consultations for data & science needs report in Q2-Q4 2026, Q1 2027
Consolidate progress & update Implementation Plan for IOC-GA 2027

## Slide 9
Timeline |  | Milestone Deliverables
Q3-Q4 2025 | A.1 A.2 | Initial Fundraising; Team Set Up; COP30 adoption; 1st WG Expert Meeting Velux; Tiffany & Co Foundation; GEF Launch communication (website)
Q1 2026 | A.2 A.4 | Communication plan & initial outreach materials finalized; initial good practices summarized/dissiminated Fundraising (cont)
Q2 2026 | A.1 A.2 A.3 A.4 | Regional meeting LAC/Caribbean (March); First in-country training; preliminary summary data needs/gaps; 2nd WG meeting April-May Fundraising (cont) Implementation communication plan (cont)
Q3 2026 | A.5 A.1-A.4 | Pilot project commences; regional meeting Asia (June); biodiversity & climate expert meeting; draft technical guidance & training; Our Ocean Conference Fundraising (cont) Implementation communication plan (cont)
Q4 2026 | A.1 A.3 A.4 A.5 | Regional meeting Africa Fundraising (cont)
Q1 2027 | A.1 A.3 A.4 A.5 | Regional meeting Indian Ocean; prep for data needs report; WG meeting Mar-April Fundraising (cont) Implementation communication plan (cont)
Q2 2027 | A.4 A.5 | Preparation reporting IOC-GA; complete guidance; update implementation plan 2028-2030 Fundraising (cont) Implementation communication plan (cont)
Q3 2027 | A.3 | Data needs report completed; start implementation new biennium plans Fundraising (cont) Implementation communication plan (cont)
Q4 2027 | A.1-A.5 | WG Meeting (Nov-Dec) implementation post 34th IOC-AG

## Slide 10: IOC-SOPM Webpages & Ocean Expert Directory
www.ioc.unesco.org/en/ioc-sopm-strategy
OceanExpert - A Directory of Marine and Freshwater Professionals

## Slide 11: Discussion & Task Force Groups
Terms of Reference under development.

## Slide 12: Any Other Business

## Slide 13: Closure