## CARIBE-EWS ACTION MONITOR
ACTION CODE | ACTION DESCRIPTION | REFERENCE | LEAD | DEADLINE | COMPLETION | STATUS | COMMENTS | REVIEW NOTES
C-2025-05-05 | Conduct a literature review study on real-time detection of submarine landslides | ICG/CARIBE-EWS XVIII | WG1, WG2 | 2026-Q2 |  | NOT STARTED
C-2025-05-06 | Consider organizing an Expert Meeting on Seismic and Non-Seismic Probabilistic Tsunami Hazard Assessment (PTHA) in the Caribbean and its Adjacent Regions | ICG/CARIBE-EWS XVIII | WG1, TS | 2026-Q4 |  | NOT STARTED
C-2025-05-07 | Circulate the monthly PTWC status maps which are also posted on the ITIC-CAR website to the TNCs for further dissemination to the (seismic and sea-level) station operators, and further requests the TNCs to inform the Working Group 2 Chair and Secretariat on plans for repair | ICG/CARIBE-EWS XVIII | WG2, TNCs, TS | N/A |  | NOT STARTED
C-2025-05-08 | Develop a tool to assess the impact of sea level station outages and include the impact of these outages in the monthly reports | ICG/CARIBE-EWS XVIII | WG2 | 2026-Q2 |  | NOT STARTED
C-2025-05-16 | Review existing national and local SOPs and provide a report for the ICG XIX. | ICG/CARIBE-EWS XVIII | WG3 | 2026-Q2 |  | NOT STARTED
C-2025-05-19 | Evaluate the feasibility and desirability of establishing a National Tsunami Ready Focal Point which could be the Chair of the National Tsunami Ready Board | ICG/CARIBE-EWS XVIII | SC, WG4, TT-TR | 2026-Q2 |  | NOT STARTED
C-2025-05-26 | Inform the UNDRR on the date of CARIBE WAVE 26 and request the theme of the WTAD 26 in advance of the exercise | ICG/CARIBE-EWS XVIII | TS, TT-CW | 2025-Q3 |  | NOT STARTED
C-2025-05-28 | Explore opportunities to further involve national and regional maritime and port authorities so they may exercise their plans and procedures | ICG/CARIBE-EWS XVIII | TT-CW, CTIC, ITIC-CAR | 2026-03 |  | NOT STARTED
C-2025-07-01 | Invite Argentina to actively participate in all organizational and implementation stages of any scientific workshop carried out to assess the potential tsunamigenic risk of the Scotia Arc | IOC/A-33 | TS | 2027-Q2 |  | NOT STARTED
C-2025-07-02 | Establish arrangements among Tsunami Service Providers (TSP) to ensure that service provision is ensured at all times for the full Area of Service of the ICG | IOC/A-33 | TSPs | 2027-Q2 |  | NOT STARTED
C-2025-05-02 | Organize a workshop dedicated on the development of SOPs between Volcano Observatories in the Caribbean and the ICG CARIBE-EWS TSPs and NTWCs | ICG/CARIBE-EWS XVIII | WGs, TS | 2026-Q2 |  | NOT STARTED
C-2024-02-01 | Revamp CTIC Board Meetings | MTOM 2024/02 | CTIC, TS, CZMU | 2024-06 |  | IN PROGRESS
C-2024-05-10 | Develop a strategic plan to mobilize funding and in-kind support for more effective Tsunami Warning and Dissemination with a particular focus for LDCs and SIDS. | ICG/CARIBE-EWS XVII | SC, TS, WG3 | 2025-05 |  | IN PROGRESS
C-2024-05-11 | PRSN to host a workshop on Evacuation Mapping. | ICG/CARIBE-EWS XVII | PRSN, WG4, TS | 2024-12 |  | IN PROGRESS
C-2025-05-01 | Organize a regional webinar for TGVs | ICG/CARIBE-EWS XVIII | WGs, TS | 2025-Q4 |  | IN PROGRESS
C-2025-05-15 | PTWC and CATAC to coordinate among each other and conduct communication tests which should start following a notification to Member States with the instructions and PTWC and CATAC report the results of these communication tests to WG 3 and present to the ICG. | ICG/CARIBE-EWS XVIII | CATAC, PTWC, WG3 | 2026-Q2 |  | IN PROGRESS
C-2023-04-04 | Initiate contacts with the identified volcano observatories and/or institutes responsible for monitoring volcanoes threatening the CARIBE-EWS, to implement the MoU with the VONUT | ICG/CARIBE EWS-XVI | WG2, TS | 2024-06 |  | IN PROGRESS
C-2025-05-29 | Explores additional opportunities to promote enhanced participation and use of the template by amateur radio operators | ICG/CARIBE-EWS XVIII | TT-CW, CTIC, ITIC-CAR | 2026-03 |  | IN PROGRESS | Issued the CL
C-2025-05-03 | Develop a plan towards ensuring the sustainability of the implementation of the UNESCO-IOCs Tsunami Ready Recognition Program in the Caribbean and its Adjacent Regions | ICG/CARIBE-EWS XVIII | SC, TS, CTIC, ITIC-CAR | 2026-Q2 |  | IN PROGRESS
C-2023-04-01 | CATAC to act as a regional real-time seismic data aggregator/hub for Central America | ICG/CARIBE EWS-XVI | CATAC | 2024-12 |  | IN PROGRESS | CATAC is expected to report to the SC in its 2025/01 meeting.
C-2023-04-02 | Conduct a study to demonstrate improvement in tsunami early warning times with two to four variations on SMART Cable designs | ICG/CARIBE EWS-XVI | WG2 | 2024-12 |  | IN PROGRESS | WG2 reported to the SC in its 2025/01 meeting.
C-2023-04-03 | Engage industry to understand which telecommunications cables are scheduled for replacement or new installations | ICG/CARIBE EWS-XVI | WG2, TS | 2024-06 |  | IN PROGRESS | WG2 reported to the SC in its 2025/01 meeting. Please also see C-2024-02-18.
C-2023-04-06 | Organize an Experts Meeting on “Non-Seismic Sources of Tsunamis for the Caribbean and Adjacent Regions" | ICG/CARIBE EWS-XVI | WG1, TS | 2024-12 | 2024-12 | IN PROGRESS | Organized in Hedia-Costa Rica during 3-5 December 2024. The report is expected to be published in 2025/Q3.
C-2023-04-07 | Execute a regional training on the development of Digital Elevation Models (DEM) for tsunami inundation modelling | ICG/CARIBE EWS-XVI | WG1, TS | 2026-Q2 |  | IN PROGRESS
C-2023-04-08 | Organize and conduct a Meeting of Experts for Seismic Sources in the Northwest Caribbean | ICG/CARIBE EWS-XVI | WG1, TS | 2024-12 |  | IN PROGRESS | Organized in Hedia-Costa Rica during 3-5 December 2024. The report is expected to be published in 2025/Q3.
C-2023-04-11 | Coordinate the posting and distribution of the current version of the CARIBE-EWS Tsunami Signage Inventory and Report and provide an updated version for the next ICG session | ICG/CARIBE EWS-XVI | ITIC-CAR,CTIC,TS | 2024-05 | 2024-05 | IN PROGRESS | Received the updated Tsunami Signage Inventory and Report and need to present it for the next ICG session
C-2023-04-13 | Final admission of CATAC as TSP in June 2024 | ICG/CARIBE EWS-XVI | ICG/CARIBE EWS | 2025-05 |  | IN PROGRESS
C-2023-04-14 | The ICG also recommended TOWS-WG to identify a mechanism to cross credit other Members States assessment, preparedness, and response efforts with the UNESCO-IOC TRRP. | ICG/CARIBE EWS-XVI | TOWS-WG | 2024-12 |  | IN PROGRESS | TOWS-WG-XVIII appreciated the progress made for establishing the Tsunami Ready Equivalency for the PTWS by developing a draft guidance using the Tsunami Ready indicators as a foundation. ICG/PTWS XXXI approved the provisional PTWS Tsunami Ready - Equivalency Guidance for piloting.
C-2024-02-04 | Haiti will communicate National Office of Civil Aviation (OFNAC) as a TWFP-Alternate | MTOM 2024/02 | Chair | 2024-05 |  | IN PROGRESS | No such communication room place yet. G. Metayer is expected to report to the SC in its 2025/01 meeting.
C-2024-02-07 | Clarifications will be requested at the TOWS-WG-XVII meeting on the KPI reporting with respect to ODTP | MTOM 2024/02 | TOWS-WG Rep, TS | 2024-02 |  | IN PROGRESS | Progress has been presented during the ODTP-SC-5 (16-17 January 2025), Denis (Focal Point)
C-2024-02-17 | Identify the venue and dates of the regional training on the development of Digital Elevation Models for tsunami inundation modelling | MTOM 2024/02 | WG1, TS | 2026-Q2 |  | IN PROGRESS | See action in the C-2023-04-07
C-2024-02-18 | Organize a SMART Cable webinar targeting the Caribbean Region | MTOM 2024/02 | WG2, TS | 2024-06 |  | IN PROGRESS
C-2024-05-02 | Formation of a sub-group under Working Group 2 to specifically address the implementation of such technology in the CARIBE-EWS. | ICG/CARIBE-EWS XVII | WG2 | 2024-12 |  | IN PROGRESS
C-2024-05-03 | Revamp the initiative for Group of Experts (GoE) on work and implementation plan to enhance the warning system by including other coastal hazards and adopted Recommendation ICG/CARIBE-EWS-XII.7. | ICG/CARIBE-EWS XVII | SC, TS | 2024-12 |  | IN PROGRESS
C-2024-05-06 | Organize an event back-to-back with ICG/CARIBE-EWS XIX in close coordination with IOCARIBE, WMO, UNDRR and other stakeholders to promote accomplishments of the ICG/CARIBE-EWS. | ICG/CARIBE-EWS XVII | SC, Barbados, TS, Curacao | 2025-08 |  | IN PROGRESS
C-2024-05-08 | Review and revise Technical, Logistical and Administrative Requirements of a Regional Tsunami Service Provider for CARIBE-EWS and present at its XVIII session at the latest | ICG/CARIBE-EWS XVII | WG3, Steering Committee | 2025-05 |  | IN PROGRESS
C-2024-05-09 | Explore and inform at ICG/CARIBE-EWS XVIII the integration of EEW applications for disseminating its tsunami services and products to its TWFP and NTWCs. | ICG/CARIBE-EWS XVII | CATAC | 2025-05 |  | IN PROGRESS
C-2024-05-13 | Evaluate the implementation process of the Tsunami Ready Evaluation Form in ICG/CARIBE-EWS and informs the ICG/CARIBE-EWS in the implementation of this effort in other ICGs in accordance with the TOWS-WG-XVII recommendation | ICG/CARIBE-EWS XVII | SC, TS, TT-TTR, WG4 | 2025-05 |  | IN PROGRESS | This will be considered during the upcoming TOWS-WG Meetings in 2025/02. TOWS-WG Representatives of the ICG/CARIBE-EWS will inform the ICG/CARIBE-EWS XVIII.
C-2024-05-14 | Organize a joint training on Manuals and Guides 86 and CARIBE WAVE Task Team meeting in Antigua and Barbuda | ICG/CARIBE-EWS XVII | CTIC, ITIC-CAR, WG4, TT-CW | 2025-05 |  | IN PROGRESS
C-2024-05-18 | Explore opportunities to further involve national and regional maritime and port authorities in the CARIBE WAVE 25 so they may exercise their plans and procedures. | ICG/CARIBE-EWS XVII | TT-CW | 2024-12 |  | IN PROGRESS
C-2024-05-23 | Consider organizing the 2nd Tsunami Ready Summit back-to-back to the ICG/CARIBE-EWS XVIII to review the benefits and lessons learned and establish a road map towards 100% communities prepared for and resilient to tsunamis through efforts like Tsunami Ready | ICG/CARIBE-EWS XVII | WG4, CTIC,TT-TR, TS | 2025-05 |  | IN PROGRESS | Tsunami Ready Summit will be held during the ICG/CARIBE-EWS
C-2025-05-12 | CATAC to submit to Working Group 3 an updated User’s Guide for CATAC Procedures and Products for the CARIBE-EWS by the end of 2025 | ICG/CARIBE-EWS XVIII | CATAC, WG3, TS | 2025-12 |  | IN PROGRESS
C-2025-05-13 | PTWC to create an annex to the User's Guide with a description of the Maritime Products | ICG/CARIBE-EWS XVIII | PTWC | 2025-12 |  | IN PROGRESS | See C-2025-05-14
C-2025-05-14 | PTWC to coordinate a start date for the implementation of the Maritime Products with the NAVAREAs by the end of 2025 and also test in CARIBE WAVE 26 - the Secretariat will inform the concerned NAVAREA IV and V Coordinators accordingly | ICG/CARIBE-EWS XVIII | PTWC, TS |  |  | IN PROGRESS
C-2025-05-20 | Prioritise completion of outstanding TRRP projects in Barbados, Grenada, Jamaica and Trinidad and Tobago | ICG/CARIBE-EWS XVIII | CTIC, TS, TT-TR | 2026-Q2 |  | IN PROGRESS | Grenada in January 2026, Barbados and Trinidad and Tobago expected to resume in January 2026 with the support from the ITIC-CAR.
C-2025-05-23 | Identify actions arising from CARIBE WAVE 25 and past CARIBE WAVE Exercises and identify follow up actions | ICG/CARIBE-EWS XVIII | SC, TT-CW,CTIC, ITIC-CAR | 2025-Q4 |  | IN PROGRESS
C-2025-05-27 | Explore opportunities to further involve tourists and tourism organizations such as the Caribbean Tourism Organization (CTO), in CARIBE WAVE exercises, with the aim to develop multilingual guidelines/resources for the involvement of tourists in CARIBE WAVE Exercises | ICG/CARIBE-EWS XVIII | TT-CW, CTIC, ITIC-CAR | 2026-03 |  | IN PROGRESS

## OVERVIEW
CARIBE-EWS ACTION MONITOR OVERVIEW
2026-05-01 | COMPLETED | IN PROGRESS | DELAYED | FAILED | NOT STARTED | CANCELED | TOTAL
# | 0 | 36 | 0 | 0 | 11 | 0 | 47
% | 0 | 76.5957 | 0 | 0 | 23.4043 | 0 | 100