Agenda Item 4.2

Working Group 2: Tsunami Detection, Analysis and Forecasting

This document presents the activities, recommendations, conclusions and a proposed work plan of Working Group2: Tsunami Detection, Analysis and Forecasting. The ICG is requested to consider, comment and eventually endorse the recommendations issued by Working Group 2.

- Introduction – Terms of Reference Purpose:

Working Group 2 aims to review and recommend to the ICG priorities and actions required to ensure and enhance existing capabilities, as well as explore new technologies to improve tsunami detection and forecasting capability.

Its tasks include:

- Source detection, identification and characterisation

  - Ensure the effectiveness of the observational system by promoting the open exchange of seismic and other relevant data in real time.

  - Advise Member States on the monitoring and detection capabilities of tsunamigenic sources needed for operating national tsunami warning centres.

  - Assure the compliance with the agreed standards for the detection systems.

- Wave detection

  - Ensure the effectiveness of the observational system by promoting the open exchange of sea level data in real time.

  - Advise Member States on the tsunami monitoring and detection capabilities needed for operating national tsunami warning centres.

  - Assure the compliance with the agreed standards for the tsunami detection systems.

- Forecasting

  - Define the operational requirements for the monitoring and forecasting systems.

  - Provide guidance on tsunami forecasting tools to Tsunami Service Providers (TSPs), National Tsunami Warning Centres (NTWCs) and provide actionable information to emergency managers.

  - Explore, experiment and test novel approaches for tsunami forecasting.

- Working Group 2 Activities:

Actions and Updates:

    - WG2 hosted an in person sea level training with the support of NOAA, IHO, NOC, and the secretariat in Barbados in Fall 2025.

    - WG2 Chair met with Smart Cable members to initiate a closer partnership and explore test geometries. Arangements for a Smart Cable webinar are in progress and planned for May 2026.

    - A code has been developed to calculate the state of health of the Caribe EWS seismic station based upon earthquake detection time. The code is based on open-source python codes (ObsPy and PyGMT) and based upon the receipt of the PTWC text monthly report. The code can be adapted for other text reports or test geometries of future installations; the open source code is available on GitHub.

WG2 Action Status:

| Action Description | Status |
| --- | --- |
| Develop a tool to assess the impact of sea level station outages and include the impact of these outages in the monthly reports | Not Started: Contact to SHOA if SHOA is interested in developing the tools and maps |
| Circulate the monthly PTWC status maps which are also posted on the ITIC-CAR website to the TNCs for further dissemination to the (seismic and sea-level) station operators, and further requests the TNCs to inform the Working Group 2 Chair and Secretariat on plans for repair | Not Started: System dependent on reception of reports and then running codes for network perfomance. |
| Conduct a study to demonstrate improvement in tsunami early warning times with two to four variations on SMART Cable designs | In Progress: Code Developed for Seismic Detection; Code distributed on GitHub. Multiple designs shared with SMART JTF. |
| Engage industry to understand which telecommunications cables are scheduled for replacement or new installations | In Progress: A Caribe SMART working group has been established including the ITU/CTU. |
| Organize a SMART Cable webinar targeting the Caribbean Region | In Progress: WG2 Chair in contact with the representatives of the SMART Subsea Cables JTF. Webinar scheduled for May 2026. |
| Formation of a sub-group under Working Group 2 to specifically address the implementation of such technology in the CARIBE-EWS. | In Progress: WG2 Chair in contact with the representatives of the SMART Subsea Cables JTF. CARIBE-EWS represented as part of the SMART WG in the Caribe. |
| Organize a training course to be taught in English on the general principles of installation and maintenance of sea level stations and the use of tide gauge data | Completed: English Language Sea level training course hosted in Barbados in 2025. |
| Organize sea level training courses in English and Spanish languages in alternating years with the support of NOAA and the Secretariat, and in close collaboration with the International Hydrographic Organization (IHO) and the International Maritime Organization (IMO). | In Progress: Evaluate if frequency sustainable; new working group to be formed for a Spanish language course. |

Draft Recommendations for ICG/CARIBE EWS XV

- Notes and appreciates the member States role of network operators in the region for the installation, maintenance, and data transmission from seismic, sea level and GNSS stations in the region

- Appreciates the NOAA ITIC-CAR, PTWC and Earthscope for improving the automated processing and continued reporting on the status of seismic and sea level stations;

- Notes that a high percentage of the stations in the CARIBE-EWS sea level network are currently non-operational and therefore can delay the proper assessment of tsunami events and the issuance of timely and accurate tsunami alerts;

- Urges Member States and operators of sea level stations contributing to CARIBE EWS to maintain their sea-level stations in an operational status and regularly review and update the status of its stations,  in the IOC Sea Level Monitoring Facility, and inform ITIC-CAR and Secretariat on plans for repair;

- Notes the development of a tool to assess impact of seismic outages in the region;

- Recommends the development of a similar tool to assess the impact of sea level station outages.

- Appreciates the work of the UN Ocean Decade on smart cables and efforts to quantify the impact of SMART cables on regional detection of tsunamigenic events and;

- Recognizing that SMART cable technology potentially impact ocean observations beyond tsunami hazard;

- Recommends Caribe-EWS participation in a Caribbean working group including stakeholders from other ocean observatories and interests to specifically address the implementation of such technology in the Caribe-EWS and formalize relationships between the Caribe-EWS and the ITU/WMO/UNESCO-IOC Joint Task Force (JTF) on SMART Cables.

- Further Encourages Member States to incorporate SMART capability into new subsea telecom cable projects.

- Recognizing and Appreciating the success of the English Language sea level training in Barbados and;

- Appreciating the efforts of the NOAA, IHO, NOC, and the secretariat to secure support for an English sea level training and;

- Appreciating the efforts of English sea level training organizing committee and regional partners in the planning and organization of such a training.

- Recommends that WG2 organize a Spanish language sea level station workshop with the support of NOAA, IHO, IMO, and the secretariat in 2027.